## Sheet1
Sprint | Planned Story Points | Completed Story Points | Velocity | Team Size | Bugs Reported | Carry Forward | Notes
Sprint 21 | 34 | 32 | 32 | 6 | 4 | 2 | Stable sprint
Sprint 22 | 36 | 35 | 35 | 6 | 3 | 1 | Minor UI enhancements
Sprint 23 | 38 | 36 | 36 | 6 | 5 | 2 | API improvements
Sprint 24 | 40 | 39 | 39 | 7 | 2 | 1 | Strong team performance
Sprint 25 | 42 | 40 | 40 | 7 | 3 | 2 | Authentication enhancements
Sprint 26 | 44 | 42 | 42 | 7 | 2 | 2 | Notification service optimization